## Backlog
Date | 23/10/2020 | Week Number | 2 | Group | P3 - 2
Resource Wizard | Bruno Ramos
Priority | Task id | Estimated duration | TODO
Priority Scale:
Low | 1 | 30 minutes | General Discussion about each member's roles |  | Critical - indispensable
Critical | 2 | 30 minutes | Research and Planning around target subject |  | High - very important
Critical | 3 | 15 minutes | Information compilation regarding target's working systems |  | Medium - required
High | 4 | 30 minutes | Use case development plan layout |  | Low - not required for now
Critical | 5 | 1 hour | Use case development
Medium | 6 | 5 minutes | Github repository merging and commit

## Scrum Board
Date | 23/10/2020 | Week Number | 2 | Group | P3 - 2
Resource Wizard | Bruno Ramos | Phase | 1
Priority |  | USER STORIES (US) | TODO | IN PROGRESS | UNDER TEST | DONE | OWNER
Low |  |  | General Discussion about each member's roles |  |  | X
Critical |  |  | Research and Planning around target subject |  |  | X
Critical |  |  | Information compilation regarding target's working systems |  |  | X
High |  |  | Use case development plan layout |  |  | X
Critical |  |  | Use case development | X
Medium |  |  | Github repository merging and commit |  |  | X

## Weekly Meeting
Date | 23/10/2020 | Week Number | 2 | Group | P3 - 2
Resource Wizard | Bruno Ramos | Phase | 1
Week | Name | What I did | What I'll do next | What impedements I'm facing
2 | Bruno Ramos - Wizard | Updated backlog, scrum board and weekly meeting tables, contributed to use case development
2 | Ana Santos - Resource Manager | Gathered and compiled information requiring the target subject, contributed to use case development
2 | Tiago Fidalgo - Oracle | Filled the required report and contributed to use case development
2 | Tomas Cansado - Critic | Revised and approved each member's respective task and contributed to use case development
2 | Duarte Guerreiro - Spokesperson | Contributed to use case development and organised the scheduled meeting
3
3
3
3
3
4
4
4
4
4
5
5
5
5
5
6
6
6
6
6
7
7
7
7
7

## After Action Report
After Action Report
Project:
Date
Code
Date:
Responsible:
Observation:
Project Summary:
Analysis of Critical Tasks:
Analysis of Results:
Recommendations: