## Gantt Chart
| Date | 2020-10-23 | Week | 2 | Group | P3-2 | ADAPT THIS SHEET TO YOUR NEEDS - IT HAS INCOMPLETE EXAMPLES FILLED IN, PLEASE CLEAN THE YELLOW MESSAGES AS SOON AS THEY ARE UNDERSTOOD
| Team Oracle | Tiago Fidalgo |  |  |  |  | This file is updated in the beggining of each phase
Respo. |  |  | Date |  |  |  |  | Salary | 50 | MDS's Per Hour per team member | [7 empty] | CONSIDER THE COST OF EACH TEAM MEMBER PER HOUR IN "MDS" COIN
THE FIRST DELIVERABLE OF THIS GANNTT CHART MUST BE DONE CONSULTING THE WHOLE TEAM
Attention: | The presented estimation for the duration of the tasks in terms of days, only make sense after consulting the "Planned Availability report". PV per task should be calculated in this project as (Task Hours)*Salary
Section 1. PLANNED |  | This section is updated once per phase (in its beginning)
WBS NUMBER | TASK TITLE | TASK OWNER | PLANNED START DATE | PLANNED DUE DATE | PLANNED DURATION (Hours) | PLAN | [9 empty] | PHASE ONE (October) | [36 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[12 empty] | WEEK 0 |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [5 empty] | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | DURATION (Cum. Hours) | PV | PV (Acc.) |  | PREDECESSORS |  | T | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[11 empty] | Day | WEEK 0 T: 8; WEEK 0 F: 9; WEEK 0 S: 10; WEEK 0 S: 11; WEEK 1 M: 12; WEEK 1 T: 13; WEEK 1 W: 14; WEEK 1 R: 15; WEEK 1 F: 16; WEEK 1 S: 17; WEEK 1 S: 18; WEEK 2 M: 19; WEEK 2 T: 20; WEEK 2 W: 21; WEEK 2 R: 22; WEEK 2 F: 23; WEEK 2 S: 24; WEEK 2 S: 25; WEEK 3 M: 26; WEEK 3 T: 27; WEEK 3 W: 28; WEEK 3 R: 29; WEEK 3 F: 30; WEEK 3 S: 31; WEEK 3 S: 1; WEEK 4 M: 2; WEEK 4 T: 3; WEEK 4 W: 4; WEEK 4 R: 5; WEEK 4 F: 6; WEEK 4 S: 7
[11 empty] | Avail. | WEEK 0 T: #REF!; WEEK 0 F: #REF!; WEEK 0 S: #REF!; WEEK 0 S: #REF!; WEEK 1 M: #REF!; WEEK 1 T: #REF!; WEEK 1 W: #REF!; WEEK 1 R: #REF!; WEEK 1 F: #REF!; WEEK 1 S: #REF!; WEEK 1 S: #REF!; WEEK 2 M: #REF!; WEEK 2 T: #REF!; WEEK 2 W: #REF!; WEEK 2 R: #REF!; WEEK 2 F: #REF!; WEEK 2 S: #REF!; WEEK 2 S: #REF!; WEEK 3 M: #REF!; WEEK 3 T: #REF!; WEEK 3 W: #REF!; WEEK 3 R: #REF!; WEEK 3 F: #REF!; WEEK 3 S: #REF!; WEEK 3 S: #REF!; WEEK 4 M: #REF!; WEEK 4 T: #REF!; WEEK 4 W: #REF!; WEEK 4 R: #REF!; WEEK 4 F: #REF!; WEEK 4 S: #REF!
1 | Project Conception and Initiation
1.1 | Understand the project's instructions | All | 2020-10-10 | 2020-10-11 | 1 | 1 | 50 | 50 | bar: WEEK 0 T to WEEK 0 S
1.1.1 | Setup Communications plan | Team's Spokesperson | 2020-10-12 | 2020-10-13 | 1 | 2 | 50 | 100 |  | 1.1 | bar: WEEK 1 M to WEEK 1 T
1.2 | Setup Attendance Availability | Resource Manager | 2020-10-14 | 2020-10-16 | 2 | 4 | 100 | 200 |  | 1,1, 1.1.1, 1.3 | bar: WEEK 1 W to WEEK 1 F
1.3 | Setup Gantt Chart | Team's Oracle | 2020-10-13 | 2020-10-14 | 1 | 5 | 50 | 250 |  | 1.1, 1.1.1 | bar: WEEK 1 T to WEEK 1 W
1.4 | Build Scrum board | Team Wizard | 2020-10-14 | 2020-10-16 | 2 | 7 | 100 | 350 |  | 1,1, 1.1.1, 1.3 | bar: WEEK 1 W to WEEK 1 F
1.5 | Control quality of Reports | Team's Critic |  |  | 0 | 7 | 0 | 350
1.6.
1.6 | Revise Documents | All | 2020-10-14 | 2020-10-16 | 2 | 9 | 100 | 450 |  | 1,1, 1.1.1, 1.3 | bar: WEEK 1 W to WEEK 1 F
2 | Phase 1 - System's UC and Actors Elicitation |  |  |  |  | 9
2.1 | Set Sprint Backlog | All | 2020-10-17 | 2020-10-22 | 5 | 14 | 250 | 700
2.2 | Sprint 1 | All | 2020-10-22 | 2020-10-27 | 5 | 19 | 250 | 950 |  | 2.1 | bar: WEEK 1 S to WEEK 3 T
2.3 | After Action Discussion & Report Production | Team Wizard
2.4 | Revise Deliverables | Critic |  |  | 0 | 0
2.5 | Submit Deliverable | Spokesperson |  |  | 0 | 0 | bar: WEEK 0 T to WEEK 0 S
3 | Phase 2 - System Analysis |  |  |  |  | 0
3.1 | Set Sprint Backlog |  |  |  | 0 | 0
3.2 | Sprint 2 |  |  |  | 0 | 0
3.3 | After Action Discussion & Report Production |  |  |  | 0 | 0
3.4 | Revise Deliverables |  |  |  | 0 | 0 | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable |  |  |  | 0 | 0
4 | Phase 3 - System Design |  |  |  |  | 0
3.1 | Set Sprint Backlog |  |  |  | 0 | 0
3.2 | Sprint 3 |  |  |  | 0 | 0
3.3 | After Action Discussion & Report Production |  |  |  | 0 | 0
3.4 | Revise Deliverables |  |  |  | 0 | 0 | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable |  |  |  |  | 0 | bar: WEEK 0 T to WEEK 0 S
4 | Close Project | [5 empty] | #DIV/0! | #DIV/0!
4.1.
4.2 | [11 empty] | WEEK 4 W: Today
4.3
INSERT MORE ROWS IF NECESSARY
Section 2. ACTUAL |  | This section should be updated every week
WBS NUMBER | TASK TITLE | TASK OWNER | EFFECTIVE START DATE | EFFECTIVE DUE DATE | DURATION (Hours) | ACTUAL (as for the current week) | [5 empty] | WEEK 1 M: PHASE ONE (October); WEEK 7 M: PHASE THREE; WEEK 10 M: PHASE FOUR
[12 empty] | WEEK 0 |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [5 empty] | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | Done (Day) | EV | EV (Acc.) | PCT OF TASK COMPLETE | PREDECESSORS |  | T | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[11 empty] | Day | WEEK 0 T: 8; WEEK 0 F: 9; WEEK 0 S: 10; WEEK 0 S: 11; WEEK 1 M: 12; WEEK 1 T: 13; WEEK 1 W: 14; WEEK 1 R: 15; WEEK 1 F: 16; WEEK 1 S: 17; WEEK 1 S: 18; WEEK 2 M: 19; WEEK 2 T: 20; WEEK 2 W: 21; WEEK 2 R: 22; WEEK 2 F: 23; WEEK 2 S: 24; WEEK 2 S: 25; WEEK 3 M: 26; WEEK 3 T: 27; WEEK 3 W: 28; WEEK 3 R: 29; WEEK 3 F: 30; WEEK 3 S: 31; WEEK 3 S: 1; WEEK 4 M: 2; WEEK 4 T: 3; WEEK 4 W: 4; WEEK 4 R: 5; WEEK 4 F: 6; WEEK 4 S: 7
[11 empty] | Avail. | WEEK 0 T: #REF!; WEEK 0 F: #REF!; WEEK 0 S: #REF!; WEEK 0 S: #REF!; WEEK 1 M: #REF!; WEEK 1 T: #REF!; WEEK 1 W: #REF!; WEEK 1 R: #REF!; WEEK 1 F: #REF!; WEEK 1 S: #REF!; WEEK 1 S: #REF!; WEEK 2 M: #REF!; WEEK 2 T: #REF!; WEEK 2 W: #REF!; WEEK 2 R: #REF!; WEEK 2 F: #REF!; WEEK 2 S: #REF!; WEEK 2 S: #REF!; WEEK 3 M: #REF!; WEEK 3 T: #REF!; WEEK 3 W: #REF!; WEEK 3 R: #REF!; WEEK 3 F: #REF!; WEEK 3 S: #REF!; WEEK 3 S: ###; WEEK 4 M: #REF!; WEEK 4 T: #REF!; WEEK 4 W: #REF!; WEEK 4 R: #REF!; WEEK 4 F: #REF!; WEEK 4 S: #REF!
1 | Project Conception and Initiation
1.1 | Understand the project's instructions | All | 2020-10-10 | 2020-10-11 | 1 | 2020-10-11 | 50 | 50 | 100% | bar: WEEK 0 T to WEEK 0 S
1.1.1 | Setup Communications plan | Team's Spokesperson | 2020-10-12 | 2020-10-13 | 1 | 2020-10-13 | 50 | 100 | 100% | 1.1 | bar: WEEK 1 M to WEEK 1 T
1.2 | Setup Attendance Availability | Resource Manager | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | 50 | 150 | 100% | 1,1, 1.1.1, 1.3 | bar: WEEK 1 R to WEEK 1 F
1.3 | Setup Gantt Chart | Team's Oracle | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | 50 | 200 | 100% | 1.1, 1.1.1 | bar: WEEK 1 T to WEEK 1 W
1.4 | Build Scrum board | Team Wizard | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | 50 | 250 | 100% | 1,1, 1.1.1, 1.3, 1.2 | bar: WEEK 1 R to WEEK 1 F
1.5 | Control quality of Reports | Team's Critic | 2020-10-16 | 2020-10-16 | 0 | 2020-10-16 | 0 | 250 | 100%
1.6. | [7 empty] | 250 | 100%
1.6 | Revise Documents | All | 2020-10-14 | 2020-10-16 | 2 | 2020-10-16 | 100 | 350 | 100% | 1,1, 1.1.1, 1.2, 1.3, 1.4, 1.5 | bar: WEEK 1 W to WEEK 1 F
2 | Phase 1 - System's UC and Actors Elicitation
2.1 | Set Sprint Backlog | All | 2020-10-17 | 2020-10-24 | 7 | 10/24/20 | 350 | 700 | 100%
2.2 | Sprint 1 | All | 2020-10-23 |  | 0 |  |  |  | 20%
2.3 | After Action Discussion & Report Production | Team Wizard |  |  | 0 |  |  |  | 0%
2.4 | Revise Deliverables | Critic |  |  | 0 |  |  |  | 0%
2.5 | Submit Deliverable | Spokesperson |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S
3 | Phase 2 - System Analysis
3.1 | Set Sprint Backlog |  |  |  | 0 |  |  |  | 0%
3.2 | Sprint 2 |  |  |  | 0 |  |  |  | 0%
3.3 | After Action Discussion & Report Production |  |  |  | 0 |  |  |  | 0%
3.4 | Revise Deliverables |  |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable |  |  |  | 0 |  |  |  | 0%
4 | Phase 3 - System Design
3.1 | Set Sprint Backlog |  |  |  | 0 |  |  |  | 0%
3.2 | Sprint 3 |  |  |  | 0 |  |  |  | 0%
3.3 | After Action Discussion & Report Production |  |  |  | 0 |  |  |  | 0%
3.4 | Revise Deliverables |  |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable | bar: WEEK 0 T to WEEK 0 S
4 | Close Project |  |  |  |  | #REF! | #DIV/0! | #DIV/0! | #REF!
TODAY
[10 empty] | * Fill weekly - Green cells only |  | WEEK 4 W: (this line should be moved to reflect the proper day)
Section 3. Indicators | [9 empty] | Indicators
[10 empty] | PV acc. |  | WEEK 1 F: 450; WEEK 2 F: 950
[10 empty] | EV acc. |  | WEEK 1 F: 350; WEEK 2 F: 700
[10 empty] | AC acc. |  | WEEK 1 F: 500; WEEK 2 F: 650
[10 empty] | SPI |  | WEEK 1 F: 0.77778; WEEK 2 F: 0.73684
[10 empty] | CPI |  | WEEK 1 F: 0.7; WEEK 2 F: 1.0769
[10 empty] | EAC |  | WEEK 1 F: 642.8571; WEEK 2 F: 882.1429
[10 empty] | ETC |  | WEEK 1 F: 43; WEEK 2 F: 232.1429
[10 empty] | VAC |  | WEEK 1 F: -193; WEEK 2 F: 67.8571
[10 empty] | TCPI |  | WEEK 1 F: 0.7; WEEK 2 F: 1.0769
Formulas:
PLAN = [PLANNED DUE DATE]
Note on L10: number of the day in the 1st phase
Note on L11: Number of free working hours made available by the team for each day.
Note on L49: number of the day in the 1st phase
Note on L50: Number of free working hours made available by the team for each day.
Note on B62: you should not refine this task in this Gantt. The details about the sprint should be in the Scrum board, Backlog and Burndown chart. -Vasco Amaral

## Sprint Burndown Chart
[7 empty] | Date | 2020-10-23 | Week | 2 | Group | P3-2
[7 empty] | Team Oracle | Tiago Fidalgo
This sheet is meant to describe one sprint (per phase)
THE SPRINT BURNDOWN CHART
|  |  |  | Sprint Identification | 1 |  | Current Day | 2020-10-23
|  |  |  | Total Estimated Sprint Backlog | 2.9 | hrs | Average Work / Day | 1 | hrs
* You only use this chart for the tasks in the backlog and that will be achieved in the sprint, non management tasks. For example, related to modelling the system in Papyrus, OCL in USE, or detailed description of the Use Cases using the doc templates, analysis of the Uber website etc
| Actual Work |  |  | 0.3
Day | Done | Accum | Total - Done | Ideal Work Remaining |  | The Ideal backlog remaining should be a straight line
1 | 1 | 1 | 6.8 | 2.9 |  | To fill in the Done column you should insert the hours with work done according to the estimated hours per task in the Backlog
2 | 0.75 | 1.75 | 6.05 | 1.9
3 | 1.05 | 2.8 | 5 | 1.6
4 | 5 | 7.8 | 0 | 1.3
5 | 0 | 7.8 | 0 | 1
6 | 0 | 7.8 | 0 | 0.7
7 | 0 | 7.8 | 0 | 0.4
8 | 0 | 7.8 | 0 | 0.1
9 | 0 | 7.8 | 0 | -0.2
10 | 0 | 7.8 | 0 | -0.5
11 | 0 | 7.8 | 0 | -0.8
12 | 0 | 7.8 | 0 | -1.1
13 | 0 | 7.8 | 0 | -1.4
14 | 0 | 7.8 | 0 | -1.7
15 | 0 | 7.8 | 0 | -2
16 | 0 | 7.8 | 0 | -2.3
17 | 0 | 7.8 | 0 | -2.6
18 | 0 | 7.8 | 0 | -2.9
19 | 0 | 7.8 | 0 | -3.2
20 | 0 | 7.8 | 0 | -3.5
21 | 0 | 7.8 | 0 | -3.8
22 | 0 | 7.8 | 0 | -4.1
23 | 0 | 7.8 | 0 | -4.4
24 | 0 | 7.8 | 0 | -4.7
25 | 0 | 7.8 | 0 | -5
26 | 0 | 7.8 | 0 | -5.3
27 | 0 | 7.8 | 0 | -5.6
28 | 0 | 7.8 | 0 | -5.9
29 | 0 | 7.8 | 0 | -6.2
30 | 0 | 7.8 | 0 | -6.5
The sprint has a fixed duration. Fill in the table below the exact number of days, instead of 30, and adapt the formulas accordingly.
Note on F7: sprint 1,2 or 3 -Vasco Amaral
Note on E8: Total of the estimated hours of the tasks -Vasco Amaral
Note on F8: Fill in the total hours estimated -Vasco Amaral
Note on E11: Auxiliary calculations for the plot -Vasco Amaral