## ID
Lab number
Team ID
Date

## Reference Calendar
SEPTEMBER | [6 empty] | Week
S | M | T | W | T | F | S |  | Milestones
|  | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05
2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12
2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19
2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26
2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30
OCTOBER
S | M | T | W | T | F | S
|  |  |  | 2020-10-01 | 2020-10-02 | 2020-10-03
2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 1 | Announcement
2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2
2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 3
2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 4 | Milestone 1 - System Analysis (UCD)
Deliverable 1 - UCD Models + UC Templates
NOVEMBER
S | M | T | W | T | F | S
2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 5
2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 6
2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 7
2020-11-22 | 2020-11-23 | 2020-11-24 | 2020-11-25 | 2020-11-26 | 2020-11-27 | 2020-11-28 | 8 | Milestone 2 - System Design
2020-11-01 2020-11-08 2020-11-15 2020-11-22: 2020-11-29; 2020-11-02 2020-11-09 2020-11-16 2020-11-23: 2020-11-30 | Deliverable 2 - Activity Diagrams, Class Diagrams and OCL constraints
DECEMBER
S | M | T | W | T | F | S
|  | 2020-12-01 | 2020-12-02 | 2020-12-03 | 2020-12-04 | 2020-12-05 | 9
2020-12-06 | 2020-12-07 | 2020-12-08 | 2020-12-09 | 2020-12-10 | 2020-12-11 | 2020-12-12 | 10
2020-12-13 | 2020-12-14 | 2020-12-15 | 2020-12-16 | 2020-12-17 | 2020-12-18 | 2020-12-19 | 11
2020-12-20 | 2020-12-21 | 2020-12-22 | 2020-12-23 | 2020-12-24 | 2020-12-25 | 2020-12-26 | 12 | Milestone 3 - Architectural Design
2020-12-27 | 2020-12-28 | 2020-12-29 | 2020-12-30 | 2020-12-31 |  |  |  | Deliverable 3 - StateCharts, Interaction Diagrams, Component Diagrams, Deployment Diagrams
JANUARY
S | M | T | W | T | F | S
[5 empty] | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9 |  | Oral discussions
10 | 1900-01-10 | 12 | 13 | 1900-01-13 | 15 | 16 |  | Oral discussions
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30

## Communication's Plan & Tools
Date | <DATE> | Week Number | <NUMBER> | Group | <LAB-ID>
Spokesperson | <NAME>
Production
| Editor | Papyrus
| Control version | Git
Communications | (Tools to be used)
<CAN ADD MORE LINES, ONE TOOL PER LINE>
e.g. Slack, Zoom/Skype/Teams/Hangouts/...?
Collaborative documents/artefacts edition
Suggestion: Google docs and sheets for collaborative edition
Overall communications strategy. Explain how do you setup the communications plan (list of internal meetings, discussions in internal forum, etc)
<you can extend the size of this box>
Next Week communications plan (list of internal meetings, discussions in internal forum, etc)
<you can extend the size of this box>

## Gantt Chart
| Date | <DATE> | Week | <NUMBER> | Group | <LAB-ID> | ADAPT THIS SHEET TO YOUR NEEDS - IT HAS INCOMPLETE EXAMPLES FILLED IN, PLEASE CLEAN THE YELLOW MESSAGES AS SOON AS THEY ARE UNDERSTOOD
| Team Oracle | <NAME> |  |  |  |  | This file is updated in the beggining of each phase
Respo. |  |  | Date |  |  |  |  | Salary | 50 | MDS's Per Hour per team member | [7 empty] | CONSIDER THE COST OF EACH TEAM MEMBER PER HOUR IN "MDS" COIN
THE FIRST DELIVERABLE OF THIS GANNTT CHART MUST BE DONE CONSULTING THE WHOLE TEAM
Attention: | The presented estimation for the duration of the tasks in terms of days, only make sense after consulting the "Planned Availability report". PV per task should be calculated in this project as (Task Hours)*Salary
Section 1. PLANNED |  | This section is updated once per phase (in its beginning)
WBS NUMBER | TASK TITLE | TASK OWNER | PLANNED START DATE | PLANNED DUE DATE | PLANNED DURATION (Hours) | PLAN | [9 empty] | PHASE ONE (October) | [36 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[12 empty] | WEEK 0 |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [5 empty] | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | DURATION (Cum. Hours) | PV | PV (Acc.) |  | PREDECESSORS |  | T | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[11 empty] | Day | WEEK 0 T: 1; WEEK 0 F: 2; WEEK 0 S: 3; WEEK 0 S: 4; WEEK 1 M: 5; WEEK 1 T: 6; WEEK 1 W: 7; WEEK 1 R: 8; WEEK 1 F: 9; WEEK 1 S: 10; WEEK 1 S: 11; WEEK 2 M: 12; WEEK 2 T: 13; WEEK 2 W: 14; WEEK 2 R: 15; WEEK 2 F: 16; WEEK 2 S: 17; WEEK 2 S: 18; WEEK 3 M: 19; WEEK 3 T: 20; WEEK 3 W: 21; WEEK 3 R: 22; WEEK 3 F: 23; WEEK 3 S: 24; WEEK 3 S: 25; WEEK 4 M: 26; WEEK 4 T: 27; WEEK 4 W: 28; WEEK 4 R: 29; WEEK 4 F: 30; WEEK 4 S: 31
[11 empty] | Avail. | WEEK 0 T: 0; WEEK 0 F: 3; WEEK 0 S: 5; WEEK 0 S: 7; WEEK 1 M: 6; WEEK 1 T: 4; WEEK 1 W: 3; WEEK 1 R: 0; WEEK 1 F: 0; WEEK 1 S: 0; WEEK 1 S: 0; WEEK 2 M: 0; WEEK 2 T: 0; WEEK 2 W: 0; WEEK 2 R: 0; WEEK 2 F: 0; WEEK 2 S: 0; WEEK 2 S: 0; WEEK 3 M: 0; WEEK 3 T: 0; WEEK 3 W: 0; WEEK 3 R: 0; WEEK 3 F: 0; WEEK 3 S: 0; WEEK 3 S: 0; WEEK 4 M: 0; WEEK 4 T: 0; WEEK 4 W: 0; WEEK 4 R: 0; WEEK 4 F: 0; WEEK 4 S: 0
1 | Project Conception and Initiation
1.1 | Understand the project's instructions | All | 2018-03-12 | 2018-03-15 | 3 | 3 | bar: WEEK 1 F to WEEK 2 S
1.1.1 | Setup Communications plan | Team's Spokesperson | 2018-03-15 | 2018-03-16 | 1 | 4 |  |  |  | 1.1
1.2 | Setup Attendance Availability | Resource Manager | 2018-03-15 | 2018-03-21 | 6 | 10 |  |  |  | 1.1 | bar: WEEK 1 S to WEEK 3 W
1.3 | Setup Gantt Chart | Team's Oracle | 2018-03-16 | 2018-03-22 | 6 | 16 | bar: WEEK 0 T to WEEK 0 S; WEEK 1 S to WEEK 3 R
1.4 | Build Scrum board | Team Wizard | 2018-03-18 | 2018-03-22 | 4 | 20 | bar: WEEK 1 S to WEEK 3 R
1.5 | Control quality of Reports | Team's Oracle | 2018-03-19 | 2018-03-22 | 3 | 23 | bar: WEEK 3 T to WEEK 3 R
1.6. | bar: WEEK 3 F to WEEK 5 F
1.6 | Revise Documents | All | 2018-03-23 | 2018-03-23 | 0 | 23 | bar: WEEK 3 F to WEEK 5 F
2 | Phase 1 - System's UC and Actors Elicitation |  |  |  |  | 23
2.1 | Set Sprint Backlog | All | 2018-03-24 | 2018-03-28 | 4 | 27
2.2 | Sprint 1 | All | 2018-03-29 | 2018-04-02 | 3 | 30
2.3 | After Action Discussion & Report Production | Team Wizard
2.4 | Revise Deliverables | Critic |  |  | 0 | 30
2.5 | Submit Deliverable | Spokesperson |  |  | 0 | 30 | bar: WEEK 0 T to WEEK 0 S; WEEK 3 F
3 | Phase 2 - System Analysis |  |  |  |  | 30
3.1 | Set Sprint Backlog |  |  |  | 0 | 30
3.2 | Sprint 2 |  |  |  | 0 | 30
3.3 | After Action Discussion & Report Production |  |  |  | 5 | 35
3.4 | Revise Deliverables |  |  |  | 0 | 35 | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable |  |  |  | 0 | 35
4 | Phase 3 - System Design |  |  |  |  | 35
3.1 | Set Sprint Backlog |  |  |  | 0 | 35
3.2 | Sprint 3 |  |  |  | 0 | 35
3.3 | After Action Discussion & Report Production |  |  |  | 0 | 35
3.4 | Revise Deliverables |  |  |  | 0 | 35 | bar: WEEK 0 T to WEEK 0 S; WEEK 3 F
3.5 | Submit Deliverable |  |  |  |  | 35 | bar: WEEK 0 T to WEEK 0 S; WEEK 3 F
4 | Close Project | [5 empty] | 0 | 0
4.1.
4.2 | [11 empty] | WEEK 4 W: Today
4.3
INSERT MORE ROWS IF NECESSARY
Section 2. ACTUAL |  | This section should be updated every week
WBS NUMBER | TASK TITLE | TASK OWNER | EFFECTIVE START DATE | EFFECTIVE DUE DATE | DURATION (Hours) | ACTUAL (as for the current week) | [5 empty] | WEEK 1 M: PHASE ONE (October); WEEK 7 M: PHASE THREE; WEEK 10 M: PHASE FOUR
[12 empty] | WEEK 0 |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [5 empty] | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | Done (Day) | EV | EV (Acc.) | PCT OF TASK COMPLETE | PREDECESSORS |  | T | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[11 empty] | Day | WEEK 0 T: 1; WEEK 0 F: 2; WEEK 0 S: 3; WEEK 0 S: 4; WEEK 1 M: 5; WEEK 1 T: 6; WEEK 1 W: 7; WEEK 1 R: 8; WEEK 1 F: 9; WEEK 1 S: 10; WEEK 1 S: 11; WEEK 2 M: 12; WEEK 2 T: 13; WEEK 2 W: 14; WEEK 2 R: 15; WEEK 2 F: 16; WEEK 2 S: 17; WEEK 2 S: 18; WEEK 3 M: 19; WEEK 3 T: 20; WEEK 3 W: 21; WEEK 3 R: 22; WEEK 3 F: 23; WEEK 3 S: 24; WEEK 3 S: 25; WEEK 4 M: 26; WEEK 4 T: 27; WEEK 4 W: 28; WEEK 4 R: 29; WEEK 4 F: 30; WEEK 4 S: 31
Avail.
1 | Project Conception and Initiation
1.1 | Understand the project's instructions | All | 2018-03-12 | 2018-03-15 | 3 |  |  |  | 100% | bar: WEEK 1 F to WEEK 2 S
1.1.1 | Setup Communications plan | Team's Spokesperson | 2018-03-15 | 2018-03-16 | 1 |  |  |  | 100% | 1.1
1.2 | Setup Attendance Availability | Resource Manager | 2018-03-15 | 2018-03-21 | 6 |  |  |  | 90% | 1.1 | bar: WEEK 1 S to WEEK 3 W
1.3 | Setup Gantt Chart | Team's Oracle | 2018-03-16 | 2018-03-22 | 6 |  |  |  | 40% | bar: WEEK 0 T to WEEK 0 S; WEEK 1 S to WEEK 3 R
1.4 | Build Scrum board | Team Wizard | 2018-03-18 | 2018-03-22 | 4 |  |  |  | 70% | bar: WEEK 1 S to WEEK 3 R
1.5 | Control quality of Reports | Team's Oracle | 2018-03-19 | 2018-03-22 | 3 |  |  |  | 60% | bar: WEEK 3 T to WEEK 3 R
1.6. | bar: WEEK 3 F to WEEK 5 F
1.6 | Revise Documents | All | 2018-03-23 | 2018-03-23 | 0 |  |  |  | 50% | bar: WEEK 3 F to WEEK 5 F
2 | Phase 1 - System's UC and Actors Elicitation
2.1 | Set Sprint Backlog | All | 2018-03-24 | 2018-03-28 | 4 |  |  |  | 22%
2.2 | Sprint 1 | All | 2018-03-29 | 2018-04-02 | 3 |  |  |  | 16%
2.3 | After Action Discussion & Report Production | Team Wizard
2.4 | Revise Deliverables | Critic |  |  | 0 |  |  |  | 0%
2.5 | Submit Deliverable | Spokesperson |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S; WEEK 3 F
3 | Phase 2 - System Analysis
3.1 | Set Sprint Backlog |  |  |  | 0 |  |  |  | 0%
3.2 | Sprint 2 |  |  |  | 0 |  |  |  | 0%
3.3 | After Action Discussion & Report Production |  |  |  | 5 |  |  |  | 0%
3.4 | Revise Deliverables |  |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable |  |  |  | 0 |  |  |  | 0%
4 | Phase 3 - System Design
3.1 | Set Sprint Backlog |  |  |  | 0 |  |  |  | 0%
3.2 | Sprint 3 |  |  |  | 0 |  |  |  | 0%
3.3 | After Action Discussion & Report Production |  |  |  | 0 |  |  |  | 0%
3.4 | Revise Deliverables |  |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S; WEEK 3 F
3.5 | Submit Deliverable | bar: WEEK 0 T to WEEK 0 S; WEEK 3 F
4 | Close Project |  |  |  |  | #REF! | 0 | 0 | #REF!
TODAY
[10 empty] | * Fill weekly - Green cells only |  | WEEK 4 W: (this line should be moved to reflect the proper day)
Section 3. Indicators | [9 empty] | Indicators
PV acc. | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F
EV acc. | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F
AC acc. | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F
SPI | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F
CPI | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F
EAC | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F
ETC | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F
VAC | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F
TCPI | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F

## Sprint Burndown Chart
[7 empty] | Date | <DATE> | Week | <NUMBER> | Group | <LAB-ID>
[7 empty] | Team Oracle | <NAME>
This sheet is meant to describe one sprint (per phase)
THE SPRINT BURNDOWN CHART
|  |  |  | Sprint Identification |  |  | Current Day
|  |  |  | Total Estimated Sprint Backlog | 450 | hrs | Average Work / Day | 15 | hrs
* You only use this chart for the tasks in the backlog and that will be achieved in the sprint, non management tasks. For example, related to modelling the system in Papyrus, OCL in USE, or detailed description of the Use Cases using the doc templates, analysis of the Uber website etc
| Actual Work |  |  | 15.5
Day | Done | Accum | Total - Done | Ideal Work Remaining |  | The Ideal backlog remaining should be a straight line
1 | 0 | 0 | 450 | 450 |  | To fill in the Done column you should insert the hours with work done according to the estimated hours per task in the Backlog
2 | 9 | 9 | 441 | 435
3 | 10 | 19 | 431 | 419.5
4 | 5 | 24 | 426 | 404
5 | 5 | 29 | 421 | 388.5
6 | 2 | 31 | 419 | 373
7 | 25 | 56 | 394 | 357.5
8 | 0 | 56 | 394 | 342
9 | 0 | 56 | 394 | 326.5
10 | 34 | 90 | 360 | 311
11 | 11 | 101 | 349 | 295.5
12 | 3 | 104 | 346 | 280
13 | 24 | 128 | 322 | 264.5
14 | 5 | 133 | 317 | 249
15 | 0 | 133 | 317 | 233.5
16 | 22 | 155 | 295 | 218
17 | 5 | 160 | 290 | 202.5
18 | 32 | 192 | 258 | 187
19 | 3 | 195 | 255 | 171.5
20 | 2 | 197 | 253 | 156
21 | 33 | 230 | 220 | 140.5
22 | 40 | 270 | 180 | 125
23 | 30 | 300 | 150 | 109.5
24 | 4 | 304 | 146 | 94
25 | 5 | 309 | 141 | 78.5
26 | 26 | 335 | 115 | 63
27 | 32 | 367 | 83 | 47.5
28 | 33 | 400 | 50 | 32
29 | 40 | 440 | 10 | 16.5
30 | 10 | 450 | 0 | 1
The sprint has a fixed duration. Fill in the table below the exact number of days, instead of 30, and adapt the formulas accordingly.

## Planned Availability
Date | <DATE> | Week Number | <NUMBER> | Group | <LAB-ID>
Resource Manager | <NAME>
EMPLOYEE ATTENDANCE TRACKER (hours per day)
October | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Mon | Tue | Wed | Thu | Fri
Employee Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Employee 1 |  | 3 | 2 | 4 | 3 | 1
Employee 2 |  |  | 2 | 2
Employee 3
Employee 4 |  |  |  |  | 3 | 3 | 3
Employee 5 |  |  | 1 | 1
TOTAL AVAILABLE HOURS | 0 | 3 | 5 | 7 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
November | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Employee Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Employee 1 |  | 3 | 2 | 4 | 3 | 1
Employee 2 |  |  | 2 | 2 | 1 | 1 | 3 | 4
Employee 3
Employee 4 |  | 2 | 2 |  | 3 | 3 | 3
Employee 5 |  |  | 1 | 1 |  | 1 | 1
TOTAL AVAILABLE HOURS | 0 | 5 | 7 | 7 | 7 | 6 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
December | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
Employee Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Employee 1 |  | 3 | 2 | 4 | 3 | 1
Employee 2 |  |  | 2 | 2 | 1 | 1 | 3 | 4
Employee 3
Employee 4 |  | 2 | 2 |  | 3 | 3 | 3
Employee 5 |  |  | 1 | 1 |  | 1 | 1
TOTAL AVAILABLE HOURS | 0 | 5 | 7 | 7 | 7 | 6 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legend |  | W | Work for Project |  | V | Other work |  | P | personal

## Attendance Tracker
Date | <DATE> | Week Number | <NUMBER> | Group | <LAB-ID>
Resource Manager | <NAME>
October | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Mon | Tue | Wed | Thu | Fri
Employee Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Employee 1 |  | 3 | 2 | 4 | 3 | 1
Employee 2 |  |  | 2 | 2 | 1 | 1 | 3 | 4
Employee 3
Employee 4 |  | 2 | 2 |  | 3 | 3 | 3
Employee 5 |  |  | 1 | 1 |  | 1 | 1
NOVEMBER | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Employee Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Employee 1 |  | 3 | 2 | 4 | 3 | 1
Employee 2 |  |  | 2 | 2 | 1 | 1 | 3 | 4
Employee 3
Employee 4 |  | 2 | 2 |  | 3 | 3 | 3
Employee 5 |  |  | 1 | 1 |  | 1 | 1
DECEMBER | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue
Employee Name | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Employee 1 |  | 3 | 2 | 4 | 3 | 1
Employee 2 |  |  | 2 | 2 | 1 | 1 | 3 | 4
Employee 3
Employee 4 |  | 2 | 2 |  | 3 | 3 | 3
Employee 5 |  |  | 1 | 1 |  | 1 | 1
Legend |  | W | Work Project |  | V | Other work |  | P | Personal |  | S | Sick

## Quality Control
Date |  | <DATE> | Week Number | <NUMBER> | Group | <LAB-ID>
Resource Manager |  | <NAME>
PLAN | [8 empty] | New
Model | Version | What Should be checked | Who is responsible for correction | Status | Corrective measure |  | Description | Corrected | Version
Use Case Diagram | 3.4 | Actors communicating whith each other | <Name> | identified error |  |  |  | yes | 3.4
Use Case 1 Description | 3.1 |  |  | checked |  |  |  |  | 3.1
Use Case 1 Description | 1.1 |  |  | undone |  |  |  |  | 1.1
Statechart 1 | 2.5 | Check for consistency between operations |  | identified error | insert the missing methods x() y() |  | The statechart is using methods that do not exist in the class diagram, or sequence |  | 2.5
Sequence Diagram |  |  |  |  | in the class Zed in the CD
Class Diagram
... |  |  |  | ignored
Added during quality control | [8 empty] | New
Model |  | What was identified as interesting to check | Who is responsible | Status | Corrective measure |  | Description | Corrected | Version
Deployment Diagram |  |  | <Name> | identified |  |  |  | yes
Use Case 1 Description |  |  |  | checked
Use Case 1 Description |  |  |  | undone

## Backlog
Date | <DATE> | Week Number | <NUMBER> | Group | <LAB-ID>
Resource Wizard | <NAME>
Below you find examples (change as necessary)
Priority | Task id | Estimated duration | TODO
| 1 | 4 | Use Case Diagram
| 2 | 12 | Use case Descriptions
| 30 |  | Activity Diagrams
| 45 |  | Class Diagram - Design
| 46 |  | OCL constraints
| 60 |  | Class Diagram - Architectural
| 70 |  | Interaction Diagrams

## Scrum Board
Date | <DATE> | Week Number | <NUMBER> | Group | <LAB-ID>
Resource Wizard | <NAME> | Phase | <NUMBER>
Priority |  | USER STORIES (US) | TODO | IN PROGRESS | UNDER TEST | DONE | OWNER
Use Case Diagram
Use case Descriptions
Activity Diagrams
5
Class Diagram - Design
OCL constraints
Class Diagram - Architectural
Interaction Diagrams
US6

## Weekly Meeting
Date | <DATE> | Week Number | <NUMBER> | Group | <LAB-ID>
Resource Wizard | <NAME> | Phase | <NUMBER>
Week | Name | What I did | What I'll do next | What impedements I'm facing
2
2
2
2
2
3
3
3
3
3
4
4
4
4
4
5
5
5
5
5
6
6
6
6
6
7
7
7
7
7

## After Action Report
After Action Report
Project:
Date
Code
Date:
Responsible:
Observation:
Project Summary:
Analysis of Critical Tasks:
Analysis of Results:
Recommendations:

## Produced Artefacts
Responsibility
Project > | Models > |  | Papyrus File provided in moodle (do not change structure)
Use Cases Diagram
Activity Diagrams
Class Diagram - Analysis
Class Diagram - Design
State Charts
Componenet Diagram
Deployment Diagram
| Code > | OCL-USE | OCL rules (inv, pre, pos)
|  | USE-Instances (failures) | Quality control (some examples/instances in USE to make them fail)
|  | USE-Instances (non-failure) | Quality control (some examples/instances in USE to pass)
Documents >
|  | UC descriptions | Templates provided in moodle
|  | Project Spreadsheet | Templates provided in moodle

## Team roles
Date | <DATE> | Week Number | <NUMBER> | Group | <LAB-ID>
Resource Manager | <NAME>
| Team Wizard | Team Critic | Resource Manager | Team Spokesman | Team Oracle
Phase
1 | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name]
2 | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name]
3 | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name] | [Number] : [First Name] [Familly Name]