## Gantt Chart
| Date | 2020-10-16 | Week | 1 | Group | P3-2 | ADAPT THIS SHEET TO YOUR NEEDS - IT HAS INCOMPLETE EXAMPLES FILLED IN, PLEASE CLEAN THE YELLOW MESSAGES AS SOON AS THEY ARE UNDERSTOOD
| Team Oracle | Tiago Fidalgo |  |  |  |  | This file is updated in the beggining of each phase
Respo. |  |  | Date |  |  |  |  | Salary | 50 | MDS's Per Hour per team member | [7 empty] | CONSIDER THE COST OF EACH TEAM MEMBER PER HOUR IN "MDS" COIN
THE FIRST DELIVERABLE OF THIS GANNTT CHART MUST BE DONE CONSULTING THE WHOLE TEAM
Attention: | The presented estimation for the duration of the tasks in terms of days, only make sense after consulting the "Planned Availability report". PV per task should be calculated in this project as (Task Hours)*Salary
Section 1. PLANNED |  | This section is updated once per phase (in its beginning)
WBS NUMBER | TASK TITLE | TASK OWNER | PLANNED START DATE | PLANNED DUE DATE | PLANNED DURATION (Hours) | PLAN | [9 empty] | PHASE ONE (October) | [36 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[12 empty] | WEEK 0 |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [5 empty] | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | DURATION (Cum. Hours) | PV | PV (Acc.) |  | PREDECESSORS |  | T | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[11 empty] | Day | WEEK 0 T: 8; WEEK 0 F: 9; WEEK 0 S: 10; WEEK 0 S: 11; WEEK 1 M: 12; WEEK 1 T: 13; WEEK 1 W: 14; WEEK 1 R: 15; WEEK 1 F: 16; WEEK 1 S: 17; WEEK 1 S: 18; WEEK 2 M: 19; WEEK 2 T: 20; WEEK 2 W: 21; WEEK 2 R: 22; WEEK 2 F: 23; WEEK 2 S: 24; WEEK 2 S: 25; WEEK 3 M: 26; WEEK 3 T: 27; WEEK 3 W: 28; WEEK 3 R: 29; WEEK 3 F: 30; WEEK 3 S: 31; WEEK 3 S: 1; WEEK 4 M: 2; WEEK 4 T: 3; WEEK 4 W: 4; WEEK 4 R: 5; WEEK 4 F: 6; WEEK 4 S: 7
[11 empty] | Avail. | WEEK 0 T: #REF!; WEEK 0 F: #REF!; WEEK 0 S: #REF!; WEEK 0 S: #REF!; WEEK 1 M: #REF!; WEEK 1 T: #REF!; WEEK 1 W: #REF!; WEEK 1 R: #REF!; WEEK 1 F: #REF!; WEEK 1 S: #REF!; WEEK 1 S: #REF!; WEEK 2 M: #REF!; WEEK 2 T: #REF!; WEEK 2 W: #REF!; WEEK 2 R: #REF!; WEEK 2 F: #REF!; WEEK 2 S: #REF!; WEEK 2 S: #REF!; WEEK 3 M: #REF!; WEEK 3 T: #REF!; WEEK 3 W: #REF!; WEEK 3 R: #REF!; WEEK 3 F: #REF!; WEEK 3 S: #REF!; WEEK 3 S: #REF!; WEEK 4 M: #REF!; WEEK 4 T: #REF!; WEEK 4 W: #REF!; WEEK 4 R: #REF!; WEEK 4 F: #REF!; WEEK 4 S: #REF!
1 | Project Conception and Initiation
1.1 | Understand the project's instructions | All | 2020-10-10 | 2020-10-11 | 1 | 1 | 50 | 50 | bar: WEEK 0 T to WEEK 0 S
1.1.1 | Setup Communications plan | Team's Spokesperson | 2020-10-12 | 2020-10-13 | 1 | 2 | 50 | 100 |  | 1.1 | bar: WEEK 1 M to WEEK 1 T
1.2 | Setup Attendance Availability | Resource Manager | 2020-10-14 | 2020-10-16 | 2 | 4 | 100 | 200 |  | 1,1, 1.1.1, 1.3 | bar: WEEK 1 W to WEEK 1 F
1.3 | Setup Gantt Chart | Team's Oracle | 2020-10-13 | 2020-10-14 | 1 | 5 | 50 | 250 |  | 1.1, 1.1.1 | bar: WEEK 1 T to WEEK 1 W
1.4 | Build Scrum board | Team Wizard | 2020-10-14 | 2020-10-16 | 2 | 7 | 100 | 350 |  | 1,1, 1.1.1, 1.3 | bar: WEEK 1 W to WEEK 1 F
1.5 | Control quality of Reports | Team's Critic |  |  | 0 | 7 | 0 | 350
1.6.
1.6 | Revise Documents | All | 2020-10-14 | 2020-10-16 | 2 | 9 | 100 | 450 |  | 1,1, 1.1.1, 1.3 | bar: WEEK 1 W to WEEK 1 F
2 | Phase 1 - System's UC and Actors Elicitation |  |  |  |  | 9
2.1 | Set Sprint Backlog | All |  |  | 0 | 9
2.2 | Sprint 1 | All |  |  | 0 | 9
2.3 | After Action Discussion & Report Production | Team Wizard
2.4 | Revise Deliverables | Critic |  |  | 0 | 9
2.5 | Submit Deliverable | Spokesperson |  |  | 0 | 9 | bar: WEEK 0 T to WEEK 0 S
3 | Phase 2 - System Analysis |  |  |  |  | 9
3.1 | Set Sprint Backlog |  |  |  | 0 | 9
3.2 | Sprint 2 |  |  |  | 0 | 9
3.3 | After Action Discussion & Report Production |  |  |  | 0 | 9
3.4 | Revise Deliverables |  |  |  | 0 | 9 | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable |  |  |  | 0 | 9
4 | Phase 3 - System Design |  |  |  |  | 9
3.1 | Set Sprint Backlog |  |  |  | 0 | 9
3.2 | Sprint 3 |  |  |  | 0 | 9
3.3 | After Action Discussion & Report Production |  |  |  | 0 | 9
3.4 | Revise Deliverables |  |  |  | 0 | 9 | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable |  |  |  |  | 9 | bar: WEEK 0 T to WEEK 0 S
4 | Close Project | [5 empty] | 0 | 0
4.1.
4.2 | [11 empty] | WEEK 4 W: Today
4.3
INSERT MORE ROWS IF NECESSARY
Section 2. ACTUAL |  | This section should be updated every week
WBS NUMBER | TASK TITLE | TASK OWNER | EFFECTIVE START DATE | EFFECTIVE DUE DATE | DURATION (Hours) | ACTUAL (as for the current week) | [5 empty] | WEEK 1 M: PHASE ONE (October); WEEK 7 M: PHASE THREE; WEEK 10 M: PHASE FOUR
[12 empty] | WEEK 0 |  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [5 empty] | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | Done (Day) | EV | EV (Acc.) | PCT OF TASK COMPLETE | PREDECESSORS |  | T | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
[11 empty] | Day | WEEK 0 T: 8; WEEK 0 F: 9; WEEK 0 S: 10; WEEK 0 S: 11; WEEK 1 M: 12; WEEK 1 T: 13; WEEK 1 W: 14; WEEK 1 R: 15; WEEK 1 F: 16; WEEK 1 S: 17; WEEK 1 S: 18; WEEK 2 M: 19; WEEK 2 T: 20; WEEK 2 W: 21; WEEK 2 R: 22; WEEK 2 F: 23; WEEK 2 S: 24; WEEK 2 S: 25; WEEK 3 M: 26; WEEK 3 T: 27; WEEK 3 W: 28; WEEK 3 R: 29; WEEK 3 F: 30; WEEK 3 S: 31; WEEK 3 S: 1; WEEK 4 M: 2; WEEK 4 T: 3; WEEK 4 W: 4; WEEK 4 R: 5; WEEK 4 F: 6; WEEK 4 S: 7
[11 empty] | Avail. | WEEK 0 T: #REF!; WEEK 0 F: #REF!; WEEK 0 S: #REF!; WEEK 0 S: #REF!; WEEK 1 M: #REF!; WEEK 1 T: #REF!; WEEK 1 W: #REF!; WEEK 1 R: #REF!; WEEK 1 F: #REF!; WEEK 1 S: #REF!; WEEK 1 S: #REF!; WEEK 2 M: #REF!; WEEK 2 T: #REF!; WEEK 2 W: #REF!; WEEK 2 R: #REF!; WEEK 2 F: #REF!; WEEK 2 S: #REF!; WEEK 2 S: #REF!; WEEK 3 M: #REF!; WEEK 3 T: #REF!; WEEK 3 W: #REF!; WEEK 3 R: #REF!; WEEK 3 F: #REF!; WEEK 3 S: #REF!; WEEK 3 S: ###; WEEK 4 M: #REF!; WEEK 4 T: #REF!; WEEK 4 W: #REF!; WEEK 4 R: #REF!; WEEK 4 F: #REF!; WEEK 4 S: #REF!
1 | Project Conception and Initiation
1.1 | Understand the project's instructions | All | 2020-10-10 | 2020-10-11 | 1 | 2020-10-11 | 50 | 50 | 100% | bar: WEEK 0 T to WEEK 0 S
1.1.1 | Setup Communications plan | Team's Spokesperson | 2020-10-12 | 2020-10-13 | 1 | 2020-10-13 | 50 | 100 | 100% | 1.1 | bar: WEEK 1 M to WEEK 1 T
1.2 | Setup Attendance Availability | Resource Manager | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | 50 | 150 | 100% | 1,1, 1.1.1, 1.3 | bar: WEEK 1 R to WEEK 1 F
1.3 | Setup Gantt Chart | Team's Oracle | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | 50 | 200 | 100% | 1.1, 1.1.1 | bar: WEEK 1 T to WEEK 1 W
1.4 | Build Scrum board | Team Wizard | 2020-10-15 | 2020-10-16 | 1 | 2020-10-16 | 50 | 250 | 100% | 1,1, 1.1.1, 1.3, 1.2 | bar: WEEK 1 R to WEEK 1 F
1.5 | Control quality of Reports | Team's Critic | 2020-10-16 | 2020-10-16 | 0 | 2020-10-16 | 0 | 250 | 100%
1.6. | [7 empty] | 250
1.6 | Revise Documents | All | 2020-10-14 | 2020-10-16 | 2 | 2020-10-16 | 100 | 350 | 100% | 1,1, 1.1.1, 1.2, 1.3, 1.4, 1.5 | bar: WEEK 1 W to WEEK 1 F
2 | Phase 1 - System's UC and Actors Elicitation
2.1 | Set Sprint Backlog | All |  |  | 0 |  |  |  | 0%
2.2 | Sprint 1 | All |  |  | 0 |  |  |  | 0%
2.3 | After Action Discussion & Report Production | Team Wizard |  |  | 0 |  |  |  | 0%
2.4 | Revise Deliverables | Critic |  |  | 0 |  |  |  | 0%
2.5 | Submit Deliverable | Spokesperson |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S
3 | Phase 2 - System Analysis
3.1 | Set Sprint Backlog |  |  |  | 0 |  |  |  | 0%
3.2 | Sprint 2 |  |  |  | 0 |  |  |  | 0%
3.3 | After Action Discussion & Report Production |  |  |  | 0 |  |  |  | 0%
3.4 | Revise Deliverables |  |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable |  |  |  | 0 |  |  |  | 0%
4 | Phase 3 - System Design
3.1 | Set Sprint Backlog |  |  |  | 0 |  |  |  | 0%
3.2 | Sprint 3 |  |  |  | 0 |  |  |  | 0%
3.3 | After Action Discussion & Report Production |  |  |  | 0 |  |  |  | 0%
3.4 | Revise Deliverables |  |  |  | 0 |  |  |  | 0% | bar: WEEK 0 T to WEEK 0 S
3.5 | Submit Deliverable | bar: WEEK 0 T to WEEK 0 S
4 | Close Project |  |  |  |  | #REF! | 0 | 0 | #REF!
TODAY
[10 empty] | * Fill weekly - Green cells only |  | WEEK 4 W: (this line should be moved to reflect the proper day)
Section 3. Indicators | [9 empty] | Indicators
[10 empty] | PV acc. |  | WEEK 1 F: 450
[10 empty] | EV acc. |  | WEEK 1 F: 350
[10 empty] | AC acc. |  | WEEK 1 F: 500
[10 empty] | SPI |  | WEEK 1 F: 0.77778
[10 empty] | CPI |  | WEEK 1 F: 0.7
[10 empty] | EAC |  | WEEK 1 F: 642.8571
[10 empty] | ETC |  | WEEK 1 F: 43
[10 empty] | VAC |  | WEEK 1 F: -193
[10 empty] | TCPI |  | WEEK 1 F: 0.699
Formulas:
PLAN = [PLANNED DUE DATE]
Note on L10: number of the day in the 1st phase
Note on L11: Number of free working hours made available by the team for each day.
Note on L49: number of the day in the 1st phase
Note on L50: Number of free working hours made available by the team for each day.
Note on B62: you should not refine this task in this Gantt. The details about the sprint should be in the Scrum board, Backlog and Burndown chart. -Vasco Amaral